## Sheet1
Feature ID | Feature Name | Category | Business Impact(1-10) | Technical Complexity(1-10) | User Sentiment (1-10) | Final Score | Priority Rank | Recommended Phase
F-001 | Smat paper recommendation | Discovery | 9 | 7 | 8 | 10 | 1 | MVP Core
F-002 | Advanced search filters | Discovery | 8 | 4 | 9 | 13 | 2 | MVP Core
F-003 | One click citation export | Productivity | 7 | 3 | 8 | 12 | 3 | MVP Core
F-004 | Collaborative annotations | Collaboration | 6 | 6 | 7 | 7 | 6 | Phase 2
F-005 | AI paper Summarization | Ai feature | 8 | 9 | 8 | 7 | 7 | Phase 3
F-006 | Reading progess Sync | User experience | 5 | 2 | 6 | 9 | 4 | MVP Core
F-007 | Social sharing integration | Social | 4 | 3 | 5 | 6 | 8 | Phase 3
F-008 | personalized research feed | Discovery | 7 | 5 | 7 | 9 | 5 | Phase 2
F-009 | Bulk paper import | Productivity | 6 | 4 | 6 | 8 | 9 | Phase 2
F-010 | Mobile offline reading | Accessibility | 5 | 7 | 6 | 4 | 10 | Phase 3

## Sheet2
Feature ID | Users Affected | Estimated Impact | Development Weeks | Expected Rentention Lift | Revenue Impact
F-001 | 85% | High | 6 | 15% | $ 25K MRR
F-002 | 92% | High | 3 | 12% | $ 18K MRR
F-003 | 78% | Medium | 2 | 8% | $ 12K MRR
F-004 | 45% | Medium | 5 | 6% | $ 8K MRR
F-005 | 65% | High | 8 | 10% | $ 20K MRR
F-006 | 70% | Low | 1.5 | 5% | $ 5K MRR
F-007 | 35% | Low | 2 | 3% | $ 3K MRR
F-008 | 60% | Medium | 4 | 7% | $ 10K MRR
F-009 | 40% | Medium | 3 | 4% | $ 6K MRR
F-010 | 55% | Medium | 6 | 6% | $ 9K MRR

## Sheet3
Feature ID | Technical Risk | Market Risk | Dependency Risk | Mitigation Risk
F-001 | Medium | Low | Medium | Start with simple collaborative filtering
F-002 | Low | Low | Low | Use existing search infrastructure
F-005 | High | Medium | High | Partner with established AI API providers
F-010 | Medium | Medium | Medium | Progressive Web app as fallback